## Estimates
M1
Issue Number | Summary of tasks | Status | Estimator | Estimated Effort (hours) | Coding Effort (hours) | Non-Coding Effort (hours) | Implementors
1 | Implement landing page | Done | Nathan Vogel | 5 | 2 | 1 | Nathan Vogel
1 | Navbar/landing page | Done | Nathan Vogel | 1 | 2 | 3 | Nathan Vogel
1 | Overview/landing page | Done | Nathan Vogel | 3 | 2 | 2 | Nathan Vogel
1 | Footer/landing page | Done | Nathan Vogel | 1 | 2 | 2 | Nathan Vogel
2 | m1/hero-section | Done | Koichiro Amakasu | 1 | 0.3 | 0.7 | Koichiro Amakasu
3 | login/signup page | Done | Kevin Lee | 1 | 1.5 | 2 | Kevin Lee
3 | login page | Done | Kevin Lee | 0.5 | 1 | 1 | Kevin Lee
3 | signup page | Done | Kevin Lee | 0.5 | 0.2 | 1 | Kevin Lee
4 | Implement User Home Page | Done | Miron Suarez | 8 | 4 | 1 | Miron Suarez
5 | Implement Vender Home Page | Done | Chloe Teijeiro | 18 | 9 | 6 | Chloe Teijeiro
6 | Implement Admin Home Page | Done | Koichiro Amakasu | 1 | 0.3 | 0.7 | Koichiro Amakasu
4 | dashboard/user home page | Done | MIron Suarez | 4 | 4 | 1 | MIron Suarez
1 | Color Block/landing page | Done | Nathan Vogel | 1 | 1 | 1 | Nathan Vogel
2 | generate illustration or image for hero section | Done | Nathan Vogel | 1 | 1 | 0.125 | Nathan Vogel
2 | hero component done | Done | Koichiro Amakasu | 0.125 | 0 | 0.03 | Koichiro Amakasu
1 | Landing page issue01 | Done | Nathan Vogel | 0.125 | 0 | 0.03 | Nathan Vogel
6 | make prompt | Done | Koichiro Amakasu | 2 | 0 | 1 | Koichiro Amakasu
6 | check the outcome. | Done | Koichiro Amakasu | 2 | 0 | 1 | Koichiro Amakasu
7 | Implement User Profile Page | Done | Chloe Teijeiro | 15 | 6 | 3 | Chloe Teijeiro
8 | Issue 08 | Done | Kevin Lee | 0.08 | 0.03 | 0.04 | Kevin Lee
1 | fixing colors, adding the footer, and changing the logo | Done | Nathan Vogel | 0.125 | 0 | 0.03 | Nathan Vogel
5 | updated global.css | Done | Chloe Teijeiro | 0.12 | 0.03 | 0.06 | Chloe Teijeiro
5 | Vendor page error fix | Done | Nathan Vogel | 0.125 | 0 | 0.03 | Nathan Vogel
M2
Issue Number | Summary of tasks | Status | Estimator | Estimated Effort (hours) | Coding Effort (hours) | Non-Coding Effort (hours) | Implementors
24 | Implement Recipes Page | Done | Nathan Vogel | 10 | 4 | 3 | Nathan Vogel
5 | Figure out how to Deploy Vendor page onto Vercel | Done | Miron Suarez | 7 | 3 | 1.5 | Miron Suarez
9 | Create Add New Recipe Page | Done | Chloe Teijeiro | 10 | 6 | 6 | Chloe Teijeiro
10 | Create an Edit User Profile Page | Done | Chloe Teijeiro | 8 | 2 | 2 | Chloe Teijeiro
12 | update user home page | Done | Miron Suarez | 4 | 3 | 0.5 | Miron Suarez
12 | Add Kitchen tips section | Done | Miron Suarez | 2 | 0.5 | 0 | Miron Suarez
13 | Fix up navbar to be completely accurate | Done | Nathan Vogel | 3 | 0.5 | 0.5 | Nathan Vogel
13 | Add a search and recipe browser | Done | Nathan Vogel | 5 | 1 | 1 | Nathan Vogel
34 | Create a review page for Vendors | Done | Kevin Lee | 2 | 1 | 3 | Kevin Lee
34 | Create a review page for Recipes | Done | Kevin Lee | 2 | 7 | 3 | Kevin Lee
56 | fixing deployment errors | Done | Koichiro Amakasu | 3 | 1 | 2 | Koichiro Amakasu
M3
Issue Number | Summary of tasks | Status | Estimator | Non-Coding Effort (hours) | Coding Effort (hours) | Estimated Effort (hours) | Implementors
49 | Clean Up Application and Remove All “Stuff” Code | Todo | Miron Sureaz | 0 | 0.03 | 0.5 | Miron Suarez
45 | Create User Accounts and Update User Profiles | In progress | Chloe Teijeiro | 2 | 2.5 | 1.5 | Chloe Teijeiro
46 | Add Reviews for Recipes | In progress | Chloe Teijeiro, Miron Sureaz, Nathan Vogel | 1 | 0 | 1 | chloe-teijeiro, mironsuarez, ndv0gel
50 | Add Recipes for Multiple User Accounts | In progress | Chloe Teijeiro | 5 | 3 | 10 | chloe-teijeiro, koi-ama, mironsuarez, ndv0gel
53 | Add Favorite Button to Individual Recipe Pages | In progress | Chloe Teijeiro | 1 | 2 | 2 | Chloe Teijeiro
11 | Add Inline Edit Feature for Vendor Ingredients | Done | Chloe Teijeiro | 1.5 | 1 | 6 | Chloe Teijeiro
40 | Remove Hard Code Stuff in User Profile Page | Done | Chloe Teijeiro | 1 | 2 | 10 | Chloe Teijeiro
41 | Fix Add Recipe Form Submission | Done | Nathan Vogel | 0.7 | 2 | 5 | Nathan Vogel
42 | Create Individual Recipe Page | Done | Nathan Vogel | 1 | 2 | 5 | Nathan Vogel
6 | Deploy Admin Dashboard to Vercel | Done | Koichiro Amakasu | 2 | 0.5 | 1 | Koichiro Amakasu
43 | Link Vendor Ingredients to Recipes | Done | Miron Suarez | 0 | 3 | 4 | Miron Suarez
44 | Add Vendor Role and Create Vendor Accounts With Ingredients | Done | Miron Sureaz | 0 | 2 | 4 | Miron Sureaz
45 | Enable Admin Controls | Done | Koichiro Amakasu | 0.7 | 0.3 | 1 | Koichiro Amakasu
46 | fixing deployment errors | Done | Koichiro Amakasu | 0 | 1 | 2 | Koichiro Amakasu
59 | Add automated Vercel build log sharing pipeline (Cloud Run × GCS × GAS) | Done | Koichiro Amakasu | 0 | 2 | 4 | Koichiro Amakasu
51 | Update Landing Page and Navbar | Done | Nathan Vogel | 0.7 | 3 | 2 | Nathan Vogel
52 | Fix search bar display options and edit/delete privileges | Done | Nathan Vogel | 0.7 | 2 | 1 | Nathan Vogel
53 | Create Edit feature for Vendors | Done | Koichiro Amakasu | 0.5 | 0.3 | 1 | Koichiro Amakasu
54 | Remove edit button for non-account users | Done | Nathan Vogel |  | 0.5 | 1 | Nathan Vogel
74 | Fix recommended recipies on user home page | Done | Miron Suarez | 1 | 1 | 1 | Miron Suarez
55 | Blocking unauthorized access to user-profile page depends on user's account types | Done | Koichiro Amakasu | 3 | 0.3 | 1 | Koichiro Amakasu
56 | Updated UI of Admin dashboard. Too colourful. | Done | Koichiro Amakasu | 0.5 | 0.3 | 1 | Koichiro Amakasu
78 | add vendor ingredients | Done | Miron Suarez | 0.7 | 2 | 2 | Miron Suarez
34 | Create a review page for Recipes | Done | Kevin Lee, Koichiro Amakasu | 0 | 2 | 2 | Kevin Lee, Koichiro Amakasu
34 | Create a section that lists existing reviews in individual recipe pages. | Done | Koichiro Amakasu | 1 | 1 | 2 | Koichiro Amakasu
58 | Create Blob database for object storage | Done | Koichiro Amakasu | 3 | 1 | 4 | Koichiro Amakasu
58 | add object storage | Done | Koichiro Amakasu | 0.5 | 0 | 0.5 | Koichiro Amakasu
58 | add logic to upload image | Done | Koichiro Amakasu | 0.7 | 0.3 | 1 | Koichiro Amakasu
58 | Add feature that automatically changes any image uploaded into .webp and store it to the storage. | Done | Koichiro Amakasu | 1 | 1 | 2 | Koichiro Amakasu
59 | force users to put images when registering recipes. | Done | Koichiro Amakasu | 0.7 | 0.3 | 1 | Koichiro Amakasu
60 | Add average stars of reviews to recipe cards. | Done | Koichiro Amakasu | 0.25 | 0.25 | 0.5 | Koichiro Amakasu
60 | Fix UI | Done | Koichiro Amakasu | 2 | 1 | 3 | Koichiro Amakasu
60 | recommended recipes on top page. UI is too old. No design. | Done | Koichiro Amakasu | 0.25 | 0.25 | 0.5 | Koichiro Amakasu
60 | Search Recipes linked to non-existing path. | Done | Koichiro Amakasu | 0.25 | 0.25 | 0.5 | Koichiro Amakasu
60 | My Saved Recipes linked to user-profile, which shows recipe cards that is differently designed. Cards design used for lists of recipe ("/browse-recipes") should be implemented. | Done | Koichiro Amakasu | 0.25 | 0.25 | 0.5 | Koichiro Amakasu
60 | fav button should also exist inside recipe card. | Done | Koichiro Amakasu | 0.25 | 0.25 | 0.5 | Koichiro Amakasu
94 | Add a delete button for recipes | Done | Miron Suarez | 0 | 0.5 | 0.5 | Miron Suarez

## Effort Tracking
Team Member | Software Development Experience (months) | How was coding effort tracked | How was non-coding effort tracked?
Miron Suarez | 18 | esstimated + timmer on phone | esstimated + timmer on phone
Chloe Teijeiro | 8 | I recorded the start and end times for each issue, then estimated the portion of time spent on coding tasks based on brief notes taken during the issue, and summed it to calculate the total coding effort. | I recorded the start and end times for each issue, then estimated the portion of time spent on non-coding tasks based on brief notes taken during the issue, and summed it to calculate the total non-coding effort.
Nathan Vogel | 10 | I just thought about the amout of work, and how long it had taken me in the past. I did not count super precisly, and kept the amount of hours I worked on the assignment in my head. | I just thought about the amout of work, and how long it had taken me in the past. I did not count super precisly, and kept the amount of hours I worked on the assignment in my head.